## Sheet1
Risk Register
Prepared by: Larissa Goh |  |  |  |  | Date: 19/03
No. | Rank | Risk | Description | Category | Root Cause | Triggers | Mitigating Action | Risk Owner | Probability | Impact
1 | Medium | Long distance between members | The huge distances between majority of the team may create challenges when organising meetups. | Logistical | Members located in different regions | Meetup planning, travel expenses, travel time, unreliable transport | Advanced weekly schedules in place, online meetings scheduled where needed | Project Manager | Medium | High
2 | Medium | Varying levels of technical knowledge among members | All members have varying levels of technical skill required for this project. This disparity may create workload imbalances and affect team cohesion. | Training & Knowledge | Different backgrounds and technical experience | Imbalanced task completion. Reliance on particular members | Ongoing commitment to upskilling. Creating a skill matrix and detailed upskilling plan. | Team | High | High
3 | High | Unsuitable operating system | Selecting an unsuitable operating system for our project. This may lead to major issues during our testing phase, cause compatibility issues, or have performance limitations. | Technical | Lack of research | software and hardware incompatibility | In depth research and assessing project requirements. Comparing OS options | System Architect | Medium | High
4 | High | Group member quitting | Group member potentially quitting during any stage of the project. | Team Members | Personal reasons | Personal reasons | Urgent meeting to discuss changed task delegations and effect on project timeline. | Project Manager | Medium | High
5 | Low | Poor communication | Miscommunication or lack of clarity among group members | Team Members | Missed udpdates, unclear expectations, lack of structure | Low morale, unclear leadership, confusing task interperation, failing to include others or themselves | Create a team contract, encourage communication, weekly high priorty meetings that requires all members to share ideas and speak. | Project Manager | Low | High
6 | Medium | File loss & Data corruption | Important data is lost or corrupted due to hardware issues or human error. | Data | Poor backup strategy, carelessness. | System crashes, storage issues, overwriting files | Implement regular backup on cloud or local drives. Use version control such as Git. | Network Engineer | Low | Medium
7 | Medium | Sickness | Team member, mentor, and client may be unavailable due to sickness, especially going into colder months. | Health & Safety | COVID-19, infection | COVID and sickness increasing. | Enable remote collaboration is available when needed e.g Discord, Teams. Flexibility to reschedule to suit client when needed. | Project Manager | High | Medium
8 | High | D-ITG Compatibility Issues | D-ITG may not function correctly or be supported on all selected operating systems. | Technical | Software incompability | Errors during installation | Early testing on each operating system | Network Engineer | High | Medium
9 | High | Hardware Issues | Failure of critical hardware such as computers and network cards can delay testing. | Technical | Improper set up or handling, physical damage, firmware issues, | Loss of connectivity, overheating, inability to boot operating system | Perform early hardware testing, document all hardware used for quick replacement, spare equipment, in contact with IT technician | System Architect | Medium | High
10 | Low | Incomplete testing due to time contraints | Large number of test combinations may cause the team to run out of time. | Schedule | Time consuming testing and set up | Delay in router coonfigurations, tool issues | Ensure all tools and configurations are fully tested during analysis phase and divide responsibilities. | Project Manager | Low | High
11 | Medium | Inconsistent test results | Differing results between operating systems | Technical | Misconfigured routers, hardware issues | Differing results for identical tests | Standardise configuration steps, peer review setup. | System Architect | Medium | High
12 | Low | Misinterpretation of data | Team may incorrectly analyse performance data due to unfamiliarity with tools, software, or hardware | Technical | Lack of network experience | Unexpected output formats, inconsistent logs | Research tool output structures, consult mentor if unclear, align on analysis methods as a team | Network Engineer | Low | Medium