## Sheet1
Risk Register for Project Name
Prepared by: Larissa Goh |  |  |  |  | Date: 19/03
No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
1 | Medium | Long distance between members | The huge distances between multiple members may create challenges when organising meetups. | Logistical/Operational | Members located in different regions | Meetup planning, travel expenses, travel time | Advanced meeting planning, online meetings | Group | Medium | High | Open
2 | Medium | Varying levels of technical knowledge among members | All members have varying levels of technical skill required for this project. This disparity may create workload imbalances and affect team cohesion. | Training & Knowledge | Different backgrounds and technical experience | Imbalanced task completion. Reliance on particular members | Ongoing commitment to upskilling. | Group | High | High | Open
3 | High | Unsuitable operating system | Selecting an unsuitable operating system for our project. This may lead to major issues during our testing phase, cause compatibility issues, or have performance limitations. | Technical | Lack of research, | software and hardware incompatibility, | In depth research and assessing project requirements. Comparing OS options | Group | Medium | High | Open
4 | High | Group member quitting
Poor communication
File loss