## Sheet1
Risk Register v2.0
Prepared by: Larissa Goh |  |  |  |  | Date: 20/05
No. | Rank | Risk | Description | Category | Root Cause | Triggers | Mitigating Action | Risk Owner | Probability | Impact
1 | Medium | Long distance between members | The huge distances between majority of the team may create challenges when organising meetups. | Logistical | Members located in different regions | Meetup planning, travel expenses, travel time, unreliable transport | Advanced weekly schedules in place, online meetings scheduled where needed | Project Manager | Medium | High
2 | Medium | Varying levels of technical knowledge among members | All members have varying levels of technical skill required for this project. This disparity may create workload imbalances and affect team cohesion. | Training & Knowledge | Different backgrounds and technical experience | Imbalanced task completion. Reliance on particular members | Ongoing commitment to upskilling. Creating a skill matrix and detailed upskilling plan. | Team | High | High
3 | High | Unsuitable operating system | Selecting an unsuitable operating system for our project. This may lead to major issues during our testing phase, cause compatibility issues, or have performance limitations. | Technical | Lack of research | software and hardware incompatibility | In depth research and assessing project requirements. Comparing OS options | System Architect | Medium | High
4 | High | Group member quitting | Group member potentially quitting during any stage of the project. | Team Members | Personal reasons | Personal reasons | Urgent meeting to discuss changed task delegations and effect on project timeline. | Project Manager | Medium | High
5 | Low | Poor communication | Miscommunication or lack of clarity among group members | Team Members | Missed udpdates, unclear expectations, lack of structure | Low morale, unclear leadership, confusing task interperation, failing to include others or themselves | Create a team contract, encourage communication, weekly high priorty meetings that requires all members to share ideas and speak. | Project Manager | Low | High
6 | Medium | File loss & Data corruption | Important data is lost or corrupted due to hardware issues or human error. | Data | Poor backup strategy, carelessness. | System crashes, storage issues, overwriting files | Implement regular backup on cloud or local drives. Use version control such as Git. | Network Engineer | Low | Medium
7 | Medium | Sickness | Team member, mentor, and client may be unavailable due to sickness, especially going into colder months. | Health & Safety | COVID-19, infection | COVID and sickness increasing. | Enable remote collaboration is available when needed e.g Discord, Teams. Flexibility to reschedule to suit client when needed. | Project Manager | High | Medium
8 | High | D-ITG Compatibility Issues | D-ITG may not function correctly or be supported on all selected operating systems. | Technical | Software incompability | Errors during installation | Early testing on each operating system | Network Engineer | High | Medium
9 | High | Hardware Issues | Failure of critical hardware such as computers and network cards can delay testing. | Technical | Improper set up or handling, physical damage, firmware issues, | Loss of connectivity, overheating, inability to boot operating system | Perform early hardware testing, document all hardware used for quick replacement, spare equipment, in contact with IT technician | System Architect | Medium | High
10 | Low | Incomplete testing due to time contraints | Large number of test combinations may cause the team to run out of time. | Schedule | Time consuming testing and set up | Delay in router coonfigurations, tool issues | Ensure all tools and configurations are fully tested during analysis phase and divide responsibilities. | Project Manager | Low | High
11 | Medium | Inconsistent test results | Differing results between operating systems | Technical | Misconfigured routers, hardware issues | Differing results for identical tests | Standardise configuration steps, peer review setup. | System Architect | Medium | High
12 | Low | Misinterpretation of data | Team may incorrectly analyse performance data due to unfamiliarity with tools, software, or hardware | Technical | Lack of network experience | Unexpected output formats, inconsistent logs | Research tool output structures, consult mentor if unclear, align on analysis methods as a team | Network Engineer | Low | Medium
13 | Medium | Loss of interest or motivation | Team may disengage over time due to lack of progress or personal interest. | Team Culture | Self perceived pack of purpose, unclear goals, repetitive tasks | Missed deadlines, low participation, poor responsiveness | Ensure clear milestones are set, recognise achievements, rotate tasks for variety. | Team | Medium | High
14 | Low | Team conflict and disruption | Conflict or lack of support amongst team leading to strained collaboration. | Team Culture | Personality clashes, lack of trust, stress, differing goals | Teamwork avoidance, heated discussions, lack of conflict management skills | Create a conflict resolution plan/process, rotate roles, implement one-on-one check-ins. | Team | Low | High
15 | Medium | Loss of accountability in shared tasks | When responsibilities are shared, lack of clear ownership/roles leads to incomplete tasks. | Team Culture | Unclear delegation | Tasks falling through gaps, work is incomplete because no one takes explicit responsibility | Assign an owner for every task in meetings, and delegate every task clearly. | Team | Medium | Medium
16 | Low | Over-reliance on one team member | Singular person becomes the single point of success for important tasks and components, creating bottleneck and risk of failure. | Team Culture | Uneven task delegation, lack of training, avoidance due to flear of blame | Lack of progress during absence, others avoiding certain tasks, burnout | Detailed skills-matrix and upskilling plan to cross-train the team. Share knowledge, rotate tasks, and identifiy backup solutions | Team | Low | High
17 | High | Fatigue and burnout | Project pressure leads to mental exhaustion and declining performance. | Wellbeing | Unrealistic deadlines, insufficient breaks, unbalanced workload distribution, no contingency time in planning | Missed meetings, emotional detachment, quality of work declining, withdrawing from team interactions | Monitor workload, ensure 12-15 hour commitment per week is spread out, encourage flexible hours | Team | Medium | High
18 | High | Inaccurate or invalid performance results | Errors in configuration and scripting result in incorrect measurements, compromising reliability and integrity of results. | Technical | Misconfigured routers, improper tool usage, incorrect script | Unexpected or outlier results, conflicting data accross runs | Re-run all configurations outside the 95% confidence interval, test scripts on all operating systems before final runs. | System Architect | Medium | High
19 | High | Inconsistent format or presentation of results across operating systems | Results vary in format or structure across operating system evaluations, reducing comparability. | Technical | Tool output inconsistencies, lack of standardised scripts | Log files contain missing or misaligned metrics, scripts failing, file naming causing overwrite or confusion | Centralise all evaluation scripts in one location, save each test in clearly labelled folders | Team | Medium | High
20 | High | Time Synchronisation Issues | Inaccurate evaluation results due to uunsyned system clocks on devices. | Technical | Unsynchronised time across sender, router, and recevier PCs. | Mismatched timestamps in logs. | Configure Chrony NTP server on all four PCs for consistent time. | System Architect | Medium | High