## 08. Requirement Traceability Ma
Requirement Traceability Matrix
Project Name: | Network Performance Evaluation on Linux Based Operating Systems in a Physical Environment
Prepared By: | Thomas Robinson
Traceability # | Category | Requirement ID | Requirement Description | Test Case ID | Test Case Description | Status
1 | Functional | R1 | Configure Fedora, Ubuntu, and Kali Linux as software routers | EC-F1.1 | Verify installation and configuration of routing services on all three Linux distributions (Fedora, Ubuntu, and Kali) | To Do
2 |  | R2 | Implement both TCP and UDP transmission protocols | EC-F1.2 | Configure and validate both ECP and UDP traffic forwarding on all router systems | To Do
3 |  | R3 | Support both IPv4 and IPv6 addressing | EC-F1.3 | Configure dual-stack IPv4/IPv6 addressing and verify connectivity using both protocols | To Do
4 |  | R4 | Set up a four-PC network topology (1 sender, 2 routers, 1 receiver) | EC-F1.4 | Establish physical connections and verify network connectivity across the four-PC topology | To Do
5 |  | R5 | Configure dual NICs on router PCs and single NICs on sender/receiver PCs | EC-F1.5 | Verify correct NIC configuration and interface assignments on all four systems | To Do
6 |  | R6 | Perform three complete evaluation rounds, one for each operating system | EC-F1.6 | Execute full evaluation cycles with identical evaluation parameters for Fedora, Ubuntu, and Kali Linux | To Do
7 |  | R7 | Generate network traffic using iPerf or D-ITG | EC-F1.7 | Install and configure traffic generation tools and verify they produce appropriate network loads | To Do
8 |  | R8 | Evaluate with 12 specified packet sizes (128 to 1536 Bytes) | EC-F1.8 | Configure traffic generator to cycle through all 12 required packet sizes and verify data collection | To Do
9 |  | R9 | Run each evaluation configuration at least 10 times | EC-F1.9 | Execute and document 10 complete evaluation runs for each configuration combination | To Do
10 |  | R10 | Identify and re-run evaluations falling outside 95% confidence interval | EC-F1.10 | Analyse initial results, identify outliers, and verify re-evaluation of anomalous configurations | To Do
11 |  | R11 | Record throughput performance across all evaluation scenarios | EC-F1.11 | Verify throughput data collection and storage for all evaluation combinations | To Do
12 |  | R12 | All evaluations must be run 10 times each with all evaluations at 95% confidence | EC-F1.12 | Validate statistical significance of all collected data across the required number of evaluation iterations | To Do
13 |  | R13 | Record throughput performance across all evaluation scenarios | EC-F1.13 | Verify consistent throughput measurement methodology across all evaluation configurations | To Do
14 |  | R14 | Measure network delays in all evaluation configurations | EC-F1.14 | Validate latency measurement and recording across all evaluation scenarios | To Do
15 |  | R15 | Calculate jitter values throughout evaluations | EC-F1.15 | Verify jitter calculation methodology and confirm data collection in all evaluation cases | To Do
16 |  | R16 | Track packet loss rates for all evaluation cases | EC-F1.16 | Validate packet loss detection and recording mechanisms for all configurations | To Do
17 |  | R17 | Log all evaluations | EC-F1.17 | Confirm comprehensive logging system captures all required evaluation parameters and results | To Do
18 |  | R18 | Generate statistical averages using the evaluation tool | EC-F1.18 | Verify statistical processing capabilities and validate output formats | To Do
19 |  | R19 | Compile final statistical data for comparison and analysis | EC-F1.19 | Validate data aggregation procedures and verify final comparative analysis outputs | To Do
20 | Non-Functional | R1 | Results must fall within a 95% confidence interval | EC-NF1.1 | Verify statistical analysis procedures confirm 95% confidence interval for all accepted results | To Do
21 |  | R2 | Statistical validation of evaluation results | EC-NF1.2 | Audit statistical methodology and confirm validation processes for all collected metrics | To Do
22 |  | R3 | Consistent evaluation methodology across all platforms and evaluation rounds | EC-NF1.3 | Verify evaluation procedures are documented and consistently applied across all operating systems | To Do
23 |  | R4 | Evaluation environment must support the full range of packet sizes | EC-NF1.4 | Validate network infrastructure can handle all required packet sizes without fragmentation or loss | To Do
24 |  | R5 | Network infrastructure must handle required throughput levels | EC-NF1.5 | Measure maximum throughput capability of evaluation environment and verify it exceeds evaluation requirements | To Do
25 |  | R6 | Measurement tools must be precise enough to capture microsecond-level jitter | EC-NF1.6 | Calibrate and verify precision of jitter measurement tools against known reference values | To Do
26 |  | R7 | Evaluation environment must maintain consistent conditions across evaluation rounds | EC-NF1.7 | Monitor and document environmental conditions throughout evaluation to verify consistency | To Do
27 |  | R8 | Hardware configurations must remain stable throughout all evaluations | EC-NF1.8 | Implement configuration control procedures and verify hardware stability between evaluation runs | To Do
28 |  | R9 | Evaluation tools must produce repeatable results | EC-NF1.9 | Perform calibration evaluations to verify result consistency with identical input parameters | To Do
29 |  | R10 | Complete logs of all evaluation runs must be preserved | EC-NF1.10 | Audit logging system to verify comprehensive capture and secure storage of all evaluation data | To Do
30 |  | R11 | Detailed recording of evaluation configurations and parameters | EC-NF1.11 | Verify configuration documentation completeness for all evaluation scenarios | To Do
31 |  | R12 | Final deliverable must include both raw logs and statistical summaries | EC-NF1.12 | Validate output format includes both raw data logs and processed statistical summaries | To Do
32 |  | R13 | Evaluation must be organised into three distinct rounds/sprints (one per OS) | EC-NF1.13 | Verify evaluation plan organisation and implementation of separate, controlled evaluation cycles | To Do
33 |  | R14 | Consistent evaluation procedures must be followed across all sprints | EC-NF1.14 | Audit evaluation execution logs to confirm procedural consistency across all evaluation rounds | To Do
34 |  | R15 | Comparison data must allow for direct analysis between operating systems | EC-NF1.15 | Validate data normalisation and comparison methodologies for cross-platform analysis | To Do
35 | Out of Scope | R1 | Acquisition of the four PCs required for evaluation | N/A | Not applicable - outside project scope | To Do
36 |  | R2 | Physical installation and configuration of hardware | N/A | Not applicable - outside project scope | To Do
37 |  | R3 | Initial operating system installations | N/A | Not applicable - outside project scope | To Do
38 |  | R4 | Network facility and power supply | N/A | Not applicable - outside project scope | To Do
39 |  | R5 | Physical security of the evaluation environment | N/A | Not applicable - outside project scope | To Do
40 |  | R6 | Environmental controls of the evaluation facility | N/A | Not applicable - outside project scope | To Do
41 |  | R7 | Long-term maintenance of the evaluation environment | N/A | Not applicable - outside project scope | To Do
42 |  | R8 | Ongoing support for the configured systems | N/A | Not applicable - outside project scope | To Do
43 |  | R9 | Application of findings to production networks | N/A | Not applicable - outside project scope | To Do
44 |  | R10 | Performance optimisation recommendations beyond evaluation results | N/A | Not applicable - outside project scope | To Do
45 |  | R11 | Evaluation of operating systems beyond the specified three distributions | N/A | Not applicable - outside project scope | To Do
46 |  | R12 | Network configurations other than the specified topology | N/A | Not applicable - outside project scope | To Do
47 |  | R13 | Evaluation of protocols beyond TCP and UDP | N/A | Not applicable - outside project scope | To Do
48 |  | R14 | Performance evaluation at speeds exceeding gigabit Ethernet | N/A | Not applicable - outside project scope | To Do
49 |  | R15 | Addressing performance issues identified during evaluation | N/A | Not applicable - outside project scope | To Do
50 |  | R16 | Implementing changes to improve network performance | N/A | Not applicable - outside project scope | To Do
51 |  | R17 | Troubleshooting underlying hardware issues | N/A | Not applicable - outside project scope | To Do