Team Meeting

| Client: | Raymond Lutui |  |
| --- | --- | --- |
| Project: | Network Performance Evaluation on Linux Based Operating Systems |  |
| Purpose: | Reviewing portfolio and meeting minutes |  |
| Meeting called by: | Larissa Goh |  |
| Location: Online | Date: 27/10/2025 | Time: 7:30pm – 11:30pm |
| QA: Win Phyo | Version: 1.1 | Minutes Reviewed By: Thomas |

Meeting Attendees

| Attendees |  |
| --- | --- |
| Names | Representing |
| Win Phyo | Project Member |
| Larissa Goh | Project Member |
| Nathan Quai Hoi | Project Member |
| Absent |  |
| Names | Representing |
| Thomas Robinson | Project Member |
| Kylie Afable | Project Member |
| Zafar Azad | Project Member |
| Charmi Patel | Project Member |

MINUTES DETAILS

| Minutes prepared by: Larissa Goh | Minutes circulation to: Project Team |
| --- | --- |

Agenda

| # | Agenda Item Description | Owner | Time Allotted |
| --- | --- | --- | --- |
|  | Roll Call of Attendees | Larissa | 2 minutes |
|  | Team Meeting Debrief | Larissa | 5 minutes |
|  | Raise issues and/or concerns | Larissa | 10 minutes |
|  | Discussion of any important topics brought to attention | Larissa | 15 minutes |
|  | Remaining Tasks Overview | Larissa | 10 minutes |

Open Action Items/Action Items from the Previous Meeting

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
|  | Reformatting the Poster layout | Larissa | 31/10/2025 |
|  | Poster: Requirements Section | Thomas & Win | 31/10/2025 |
|  | Poster: Shortening and fixing up own sections | All team Members | 31/10/2025 |
|  | Individual Reflective Report | All Team Members | 31/10/2025 (Extended) |
|  | Organising the Portfolio folders | Thomas | 28/10/2025 |
|  | Final Poster | All Team Members | 31/10/2025 (Extended) |

Discussion and Decisions

| # | Discussion and Decisions |
| --- | --- |
|  | Teammate accidentally overwrote all our client-mentor meeting entries. Nathan, Larissa, and Win spent time restoring this while ensuring all other team meeting minutes are uploaded and updated correctly. Ensured backups are kept. |

Summary of Action Items

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
|  | Restored previous client-mentor meeting minutes. | Nathan | Completed |
|  | Ensured ALL meeting minutes for this year have been uploaded. | Nathan, Larissa, Win | Completed |
|  | Backed up entire portfolio contents. | Nathan, Win | Completed |
|  | Create a list of final changes for our meeting with the entire team tomorrow before final submission. | Larissa, Win | Completed |
|  | Reformatting the Poster layout | Larissa | 31/10/2025 |
|  | Poster: Requirements Section | Thomas, Win | 31/10/2025 |
|  | Poster: Shortening and fixing up own sections | All Team Members | 31/10/2025 |
|  | Individual Reflective Report | All Team Members | 31/10/2025 |
|  | Organising the Portfolio folders | Thomas | 28/10/2025 |
|  | Final Poster | All Team Members | 31/10/2025 |

Next Meeting

| Date: 28/10/2025 |  | Time: 5:00pm |
| --- | --- | --- |
| Discussion points for the next meeting: |  |  |
|  | Finalising everything for the final portfolio submission. |  |
| Action Items to be discussed in the next meeting: |  |  |
|  | Submitting portfolio. |  |